## Product backlog
product backlog
ID | Feature | Priority
1 | The app has to receive data from datasets | M
2 | The app has to display the data on a screen | M
3 | The app has a visually stunning design | S
4 | The app has navigation | S
5 | Tha app has a menu | S
6 | The app has a feature allowing users to change the diagrams | C
7 | The app has a search function | C
8 | The app has a filtering fuction for results | C
9 | The app has a help menu | S
10 | The app has contact information | C
11 | The app provides different language options for displaying information | W
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Sprint 1
Sprint backlog 1
ID | User story | Priority | Storypoints | Tasks | Acceptance criteria
1 | As a user i want a prototype of the app ui so i can see how to navigate through all the submenus. | S | 20 points | • Brainstorm on what aspect ratio will work best for the app. • Lookup theories surounding screen design. • Sketch UI elements keeping in mind screen ratio. • Test the storyboard navigation style. | • Screen ratio supports my desing choice. • UI elements on screen fit perfectly together. • navigation does not require to much effort from user.
2 | As a developer i want a collection of datasets so i can have data sources to receive information from. | M | 30 points | • Figure out what datasets are available for my project. • Discuss with team if datasets can be used. • Look up information surrounding datasets . • Add datasets to file collection for later use. | •Datasets are not outdated. • datasets support my data management app.
3 | As a developer i want a programming language so i can write code that receives data from collected datasets. | M | 10 points | • search for programming language for project. • download programming language for project. | • programming language is installed and ready for future use.
4 | As a developer i want a database management system so i can write queries to retreive data from the datasets. | M | 5 points | • download database management system and install it. | • database management system is installed and ready for future use.
5 | As a developer i want a set of questions that my app needs to answer so i can write queries that are meaningfull to the app users. | S | 5 points | • brainstorm about what purpose this app has. • Discuss with team how those questions relate to eachother and the database. • Look up information about the topic at hand. •present the questions to productowner for review. | • Discuss with team if datasets can be used. • Look up information surrounding datasets . • Add datasets to file collection for later use.

## Sprint 2
Sprint backlog 1
ID | User story | Priority | Storypoints | Tasks | Acceptance criteria
1 | As a developer i want a working database so i can derive information from the tables to answer my queries. | M | 10 points | • Create an erd model. • Lookup data in data sets. • Test data base for value inputs and relationships. | • Erd must show relationships and connections. • Collected data can be applied to database. • Tests should be succesfull and functions need to work. • Code doesnt cause problems with other sets.
2 | As a developer i want a working website interface so i can test the grahpics of the diagrams on. | M | 5 points | • Select the right screen size for app screen. • Lookup theories surounding score screen design. • use test color schemes to find right ui for app. | • Screen must not interfere with app ui elements. • Collected data can be applied to page. • tests should be succesfull and function need to work. • Test canvas has matching color and is readable.
3 | As a user i want a storyboard translated into a digital mockup how the website is going to behave so i know how to navigate through the pages of the webapplication. | C | 5 points | • Brainstorm on what aspect ratio will work best for the app. • Sketch UI elements are translated into digital model. • Test the page navigation . | • Screen must not interfere with the display of page elements. • User can navigation without to much clicking of mouse.
4 | As a Developer i want a program to write code in so i can add visual graphics to the webpage upon which user will be able to view data in tables on. | M | 1 point | download C# , Visualstudio , Ryder • Concept code for webpage • Rewrite code to support elements on webpage | •All programs are setup and working. • Rewritten code has no errors. • Basic navigation works.
| As a developer i want to translate my sub-questions into postgresql queries so i can derive information and put that information into tables for the users to view. | M | 5 points | • Translate erd relationships and connections into queries for database language. • Add values from datasets into tables. • Call apon values for testing. | • Erd relationships and connections work in database language. • Collected data can be called in the database. • Tables work and have enough data for visualization. • Queries dont cause problems in other tables.
| As a user i want a variation of tables on the webpage so i can view the data i want to see based on the filters i selected. | S | 4 points | • Create tables for the website in visualstudio. • Add values of queries into the tables. • Create basic filters for testing. | •Tables have data asked by user and are loaded on page. • Values have enough information to answer user question. • Filters add variation in data displayed.
| As a user i want a home button so i can return to the homepage upon which i started. | M | 3 points | • Brainstorm where to put home button. • Write code for working home button. • Test position of home button with test users. | • Home button should be visible at first glance. • Collected data from test can be used for improving home button fuction if needed. • Homebutton brings user to start screen. • Code doesnt cause problems with other page elements.
| As a user i want a help button that brings me to a help screen so i can see the developers contact information , information about the website and database . | M | 3 points | • Brainstorm where to put help button . • Brainstorm what information will be displayed when pressed. • Write code for working help button. • Test position of help button with test users. | • Help button should be visible at first glance. • Collected data from test can be used for improving help button fuction if needed. • Help brings user to information screen about webpage. • Code doesnt cause problems with other page elements.
| As a user i want a escape button so i can exit the webpage if needed. | M | 3 points | • Brainstorm where to put escape button . • Write code for working escape button. • Test position of escape button with test users. | • Escape button should close all pages from app . • Escape button should be visible at first glance.
| As a developer i want graphs best representing the subquestions so the user can have good overview of what the answers are to those questions . | M | 31 points | • Brainstorm about which graphs best fit the data that needs to be viewed. • Brainstorm what information will be displayed when selected. • Choose what the y-axis looks like and the x-axis looks like. | • The data is best represented by a particular graph. •The axes have the right information on them .

## Sprint 3
Sprint backlog 1
ID | User story | Priority | Storypoints | Tasks | Acceptance criteria
1 | As a user i want a working sub app window so i can look up de data i want to see. | M | 10 points | •Write code to create app window. •Test menu function with test group . •Write code in plugin to make ui element work. | • Code doesnt cause problems with main menu. • Test group can use the windows without happering . • tests should be succesfull and function need to work. • Code doesnt cause problems with the main app and other app windows of subgroups 2 and 1.
2 | As a user i want filters on the app so i can filter out the data i want to vizualise . | M | 10 points | • Write queries that will act as filters on the database. • Decide what data needs to be vizualized from database. • write code that adds filters to the app window. | • Queries can derive less data or more data depending on what filter is selected. • The data derived from tha database will provide enough information to answer the new filterd question. • Code of the filters doesnt cause problems with other app functions.
3 | As a user i want a graph of the questions i want answerd so i can derive my answer from the graph. | M | 10 points | • Select the right graph to represent the data. •Select other optional graph types in case main graph doesnt provide enough information to user. • Insert values into graph to draw graph. •Test graph with users to see if the info is understandable . | • Graph has y and x-axis that use the right columns. • Optional Graph can also provide the reight columns per axis but has a different vizualisation style. • Values are pulled from the the data base created by team. • Pause has to stop the game temporarily but not score. • Most user must be able to understand the info in the graphs.
5 | As a developer i want a set of queries to derive information from the database. | M | 15 points | • Write working queries . | • Qeuries are able to pull data out of more than 2 columns and more than 2 tables and perform certain mathematic tasks needed for some of the graphs.
6 | As i user i want various buttons so i can navigate through the app window. | M | 10 points | • Choose final button positions . • Edit written code for working buttons in plugin. • Test position of buttons with test users. | • All buttons should be visible at first glance to users. • Code doesnt cause problems with other page elements.
7 | As a user i want a color scheme that doesnt interfere with the navigation and the text on the screen so i can differentiate between ui elements. | M | 10 points | • Choose a set of colors for the app ui. •Design the ui in wordform . • Edit elements to not interfere with eachother. •Test color scheme on users groups using the app . | • The text on the screen needs to be readable to users. • Ui elements need a basic form so it is recognizable to any user. • Edited ui elements dont interfere with eachother in anyway. •Test color scheme is to the user liking and not to busy.
| As a user i want a bug free app so i can smoothly use the app. | M | 5 points | • Fix ui errors if needed. •Fix design errors if needed. • Fix bugs in the code . •Test color scheme on users groups using the app . | • Ui errors have all been fixed. • Design errors have all been fixed. • Bugs in code have all been fixed. •Test color scheme is accepted by many users.