## Product backlog
product backlog
ID | Feature | Priority
1 | The app has to receive data from datasets | M
2 | The app has to display the data on a screen | M
3 | The app has a visually stunning design | S
4 | The app has navigation | S
5 | Tha app has a menu | S
6 | The app has a feature allowing users to change the diagrams | C
7 | The app has a search function | C
8 | The app has a filtering fuction for results | C
9 | The app has a help menu | S
10 | The app has contact information | C
11 | The app provides different language options for displaying information | W
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Sprint 1
Sprint backlog 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a user i want a prototype of the app ui so i can see how to navigate through all the submenus. | H | 1 hour | • Brainstorm on what aspect ratio will work best for the app. • Lookup theories surounding screen design. • Sketch UI elements keeping in mind screen ratio. • Test the storyboard navigation style. | • Screen ratio supports my desing choice. • UI elements on screen fit perfectly together. • navigation does not require to much effort from user.
2 | As a developer i want a collection of datasets so i can have data sources to receive information from. | H | 2 hours | • Figure out what datasets are available for my project. • Discuss with team if datasets can be used. • Look up information surrounding datasets . • Add datasets to file collection for later use. | •Datasets are not outdated. • datasets support my data management app.
3 | As a developer i want a programming language so i can write code that receives data from collected datasets. | H | 0.5 hours | • search for programming language for project. • download programming language for project. | • programming language is installed and ready for future use.
4 | As a developer i want a database management system so i can write queries to retreive data from the datasets. | H | 0.5 hours | • download database management system and install it. | • database management system is installed and ready for future use.
5 | As a developer i want a set of questions that my app needs to answer so i can write queries that are meaningfull to the app users. | H | 1 hour | • brainstorm about what purpose this app has. • Discuss with team how those questions relate to eachother and the database. • Look up information about the topic at hand. •present the questions to productowner for review. | • Discuss with team if datasets can be used. • Look up information surrounding datasets . • Add datasets to file collection for later use.

## Sprint 2
Sprint backlog 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a developer i want a working database so i can derive information from the tables to answer my queries | H | 3 hours | • create an erd model. • Lookup data in data sets. • Test data base for value inputs and relationships. | • erd must show relationships and connections • Collected data can be applied to database • tests should be succesfull and functions need to work • Code doesnt cause problems with other sets
2 | As a developer i want a working website interface so i can test the grahpics of the diagrams on | H | 5 hours | • Select the right screen size for app screen. • Lookup theories surounding score screen design. • use test color schemes to find right ui for app. | • Screen must not interfere with app ui elements • Collected data can be applied to page • tests should be succesfull and function need to work • Test canvas has matching color and is readable
3 | As a user i want a storyboard translated into a digital mockup how the website is going to behave so i know how to navigate through the pages of the webapplication | H | 3 hours | • Brainstorm on what aspect ratio will work best for the app. • Sketch UI elements are translated into digital model • Test the page navigation . | • Screen must not interfere with the display of page elements • user can navigation without to much clicking of mouse
4 | As a Developer i want a program to write code in so i can add visual graphics to the webpage upon which user will be able to view data in tables on. | H | 10 hours | download C# , Visualstudio , Ryder • Concept code for webpage • Rewrite code to support elements on webpage | •All programs are setup and working • Rewritten code has no errors • Basic navigation works.
| As a developer i want to translate my sub-questions into postgresql queries so i can derive informtion and put that information into tables for the users to view. |  |  | • translate erd relationships and connections into queries for database language • add values from datasets into tables • call apon values for testing | • erd relationships and connections work in database language • Collected data can be called in the database • tables work and have enough data for visualization • queries dont cause problems in other tables
| As a user i want a variation of tables on the webpage so i can view the data i want to see based on the filters i selected. |  |  | • create tables for the website in visualstudio • Add values of queries into the tables • create basic filters for testing | •tables have data asked by user and are loaded on page • Values have enough information to answer user question • filters add variation in data displayed
| As a user i want a home button so i can return to the homepage upon which i started |  |  | • brainstorm where to put home button • write code for working home button • test position of home button with test users | • Home button should be visible at first glance • Collected data from test can be used for improving home button fuction if needed. • Homebutton brings user to start screen • Code doesnt cause problems with other page elements
| As a user i want a help button that brings me to a help screen so i can see the developers contact information , information about the website and database . |  |  | • brainstorm where to put help button • brainstorm what information will be displayed when pressed • write code for working help button • test position of help button with test users | • Help button should be visible at first glance • Collected data from test can be used for improving help button fuction if needed. • Help brings user to information screen about webpage • Code doesnt cause problems with other page elements
| As a user i want a escape button so i can exit the webpage if needed |  |  | • brainstorm where to put escape button • write code for working escape button • test position of escape button with test users | • escape button should close all pages from app • escape button should be visible at first glance
| As a user i want a discription section below the statistics so i have a little information about the game data i'm viewing. |  |  | • brainstorm where to put discription section on the page • brainstorm what information will be displayed when discription is pressed • write information per filter for proper display • test position of discription and information displayed with test users | • Discription should popup when statistics of queries are loaded on to page • Information needs to be brief and meaningfull • information needs to be up-to-date • test should improve information in the discription

## Sprint 3
Sprint backlog 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a user, I want a menu screen , so i have an option to exit the game. | H | 3 hours | • Select the right screen size for menu • Lookup theories surounding screen design. • Test menu function for problems . • Write menu size in pygame | • Screen must not interfere with the games display • Collected data can be applied to game • tests should be succesfull and function need to work • Test canvas is a succes • Code doesnt cause problems with other game functions
2 | As a user, i want visually stunning background graphics so i can enjoy the artstyle of the games. | H | 5 hours | • search for backgrounds that fit the theme of the game • studie obstacle behaviour with sprites • studie how obstacles effect the other code functions • Concept code for obstacles • Add background image to the sprites file | • background must not interfere with the games display • Collected data can be applied to game • tests should be succesfull and function of background need to work • Test game with new background should be flawless • Code of background doesnt cause problems with other game functions
3 | As a developer i want a pause menu so i can halt the game if needed. | H | 3 hours | • Select the right screen size for pause screen • Lookup theories surounding pause screen design. • Test pause screen function for problems . • Write pause functions in pygame | • Screen must interfere with the games display • Collected data can be applied to game • tests should be succesfull and function need to work • Pause has to stop the game temporarily but not score • Code doesnt cause problems with other game functions such as progression
4 | As a player i want i visually stunning character so i can be represented as a gamecharacter. | H | 10 hours | • search for sprite based images for character • studie obstacle behaviour with sprites • resize character to fit the game • make a map and add character image in it • test character • Rewrite code to support character | •character is the right size and fits inside the screen • character matches the theme of the game • import image file works properly • Basic Character looks visually stunning
5 | As a developer i want bugs fixed so the player can enjoy the game. | H | 40 hours | • search for bugs in the code and look what causes them • studie obstacle behaviour with sprites • studie how obstacles effect the other code functions and fix errors • test new code • Rewrite code to support the extra lines of code | • bugs surrounding code are fixed • test code is successfull • studie how obstacles effect the other code functions • test of new code is successfull and works properly
6 | As a player i want one game menu ,so i can access all the minigames from one place. | H | 20 hours | • search for bugs in the code and look what causes all games to not load • studie videos surrounding adding mutiple types of code to one file • studie how obstacles effect the other code functions and fix errors • Rewrite code to support all games at the same time | • search for bugs in the code and look what causes all games to not load can be applied to our game menue • Rewritten code to support all games at the same time works
7 | As a player i want ambient noise , i can enjoy the game sounds while playing the game in peace. | H | 2 hours | • Search for music that fits the team of the game • Add sound fuction to the game settings file | • Ambient noice volume is mild and not distracting to the player • Add sound fuction plays music when game starts