## SprintInfo
Start Date | 2018-03-20 | Enter the start date for the sprint
End Date | 2018-04-03 | Enter the ending date for the sprint
Elapsed Days | 11
Holidays | 0 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 11
Number of Devs | 6
Utilization | 30% | Enter a value for the utilization of the team
Available Dev Hours | 158.4
Daily Dev Hours | 14.4

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status
3 | 1 | 8 | Charts implementeren | Sina+Koen | 0 | Completed
3 | 5 | 8 | Charts aan de database verbinden | Sina+Koen | 0 | Completed
3 | 1 | 3 | filters bepalen en toevoegen | Sina+Koen | 0 | Completed
3 | 4 | 2 | UI toevoegen en designer | Sina+Koen | 0 | Completed
3 | 5 | 2 | Drop down menu implementeren | Malaz+Mitchel | 0 | Completed
3 |  | 2 | landen namen aan het menu toevoegen | Malaz+Mitchel |  | Completed
3 | 3 | 8 | Grafieken implementeren | Malaz+Mitchel | 0 | Completed
3 | 1 | 6 | Knopen implementeren | Malaz+Mitchel | 0 | Completed
3 | 3 | 5 | Passende grafieken gebruiken met de informatie | Malaz+Mitchel | 0 | Completed
3 | 3 | 5 | Legenda implementeren naast de grafieken | Malaz+Mitchel | 0 | Completed
3 | 5 | 2 | Drop down menu implementeren | Chofni+Joseph | 0 | Completed
3 | 2 | 8 | Grafieken implementeren | Chofni+Joseph | 0 | Completed
3 | 3 | 6 | Knopen implementeren | Chofni+Joseph | 0 | Completed
3 | 4 | 5 | Passende grafieken gebruiken met de informatie | Chofni+Joseph | 0 | Completed
Total |  | 70 |  |  | 0

## BurnDownTable
Work Day | Target Burn Down | Forecast Burn Down | Actual Burn Down
0 | 70 | 70 | 65
1 | 63.6364 | 64 | 60
2 | 57.2727 | 57 | 57
3 | 50.9091 | 51 | 50
4 | 44.5455 | 45 | 45
5 | 38.1818 | 38 | 35
6 | 31.8182 | 32 | 32
7 | 25.4545 | 25 | 24
8 | 19.0909 | 19 | 19
9 | 12.7273 | 13 | 12
10 | 6.3636 | 6 | 6
Note on A2: PowerUps for Excel: Create one row per day in the sprint.