## SprintInfo
Start Date | 2018-02-06 | Enter the start date for the sprint
End Date | 2018-03-06 | Enter the ending date for the sprint
Elapsed Days | 21
Holidays | 10 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 11
Number of Devs | 6
Utilization | 30% | Enter a value for the utilization of the team
Available Dev Hours | 158.4
Daily Dev Hours | 7.5429

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status
1 | 1 | 8 | Onderzoeken doen naar het onderwerp | iedereen | 0 | Completed
1 | 5 | 8 | Navigatie binnen de app bepalen | Sina+Koen | 0 | Completed
1 | 1 | 3 | Onderwerp kiezen | iedereen | 0 | Completed
1 | 4 | 2 | Styletiles maken | Sina+Koen | 0 | Completed
1 | 5 | 2 | Flowchart maken | Sina+Koen | 0 | Completed
1 | 3 | 8 | Designstyle kiezen | iedereen | 0 | Completed
1 | 1 | 6 | Deelvragen verzinnen | iedereen | 0 | Completed
1 | 3 | 5 | Storyboard maken | Malaz+Mitchel | 0 | Completed
1 | 3 | 5 | Storyboard maken | Chofni+Joseph | 0 | Completed
1 | 5 | 3 | Visualsatie maieren onderzoeken | Iedereen | 3 | In Progress
| 2 | 8 | Datasets vezamlen | Iedereen | 0 | Completed
| 3 |  |  |  | 0
| 4 |  |  |  | 0
Total |  | 58 |  |  | 3

## BurnDownTable
Work Day | Target Burn Down | Forecast Burn Down | Actual Burn Down
0 | 58 | 58 | 58
1 | 52.7273 | 50.4571 | 50
2 | 47.4545 | 42.9143 | 45
3 | 42.1818 | 38 | 38
4 | 36.9091 | 30 | 35
5 | 31.6364 | 25 | 25
6 | 26.3636 | 20 | 24
7 | 21.0909 | 15 | 20
8 | 15.8182 | 5 | 13
9 | 10.5455 | 5 | 10
10 | 5.2727 | 0 | 3
Note on A2: PowerUps for Excel: Create one row per day in the sprint.