## Product backlog
product backlog
ID | Feature | Priority
1 | The app has to receive data from datasets | M
2 | The app has to display the data on a screen | M
3 | The app has a visually stunning design | S
4 | The app has navigation | S
5 | Tha app has a menu | S
6 | The app has a feature allowing users to change the diagrams | C
7 | The app has a search function | C
8 | The app has a filtering fuction for results | C
9 | The app has a help menu | S
10 | The app has contact information | C
11 | The app provides different language options for displaying information | W
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Sprint 1
Sprint backlog 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a user i want a prototype of the app ui so i can see how to navigate through all the submenus. | H | 1 hour | • Brainstorm on what aspect ratio will work best for the app. • Lookup theories surounding screen design. • Sketch UI elements keeping in mind screen ratio. • Test the storyboard navigation style. | • Screen ratio supports my desing choice. • UI elements on screen fit perfectly together. • navigation does not require to much effort from user.
2 | As a developer i want a collection of datasets so i can have data sources to receive information from. | H | 2 hours | • Figure out what datasets are available for my project. • Discuss with team if datasets can be used. • Look up information surrounding datasets . • Add datasets to file collection for later use. | •Datasets are not outdated. • datasets support my data management app.
3 | As a developer i want a programming language so i can write code that receives data from collected datasets. | H | 0.5 hours | • search for programming language for project. • download programming language for project. | • programming language is installed and ready for future use.
4 | As a developer i want a database management system so i can write queries to retreive data from the datasets. | H | 0.5 hours | • download database management system and install it. | • database management system is installed and ready for future use.
5 | As a developer i want a set of questions that my app needs to answer so i can write queries that are meaningfull to the app users. | H | 1 hour | • brainstorm about what purpose this app has. • Discuss with team how those questions relate to eachother and the database. • Look up information about the topic at hand. •present the questions to productowner for review. | • Discuss with team if datasets can be used. • Look up information surrounding datasets . • Add datasets to file collection for later use.

## Sprint 2
Sprint backlog 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a user, I want a menu screen , so i have an option to exit the game. | H | 3 hours | • Select the right screen size for menu • Lookup theories surounding screen design. • Test menu function for problems . • Write menu size in pygame | • Screen must not interfere with the games display • Collected data can be applied to game • tests should be succesfull and function need to work • Test canvas is a succes • Code doesnt cause problems with other game functions
2 | As a user, i want a Create a score screen so i know how my game progression went. | H | 5 hours | • Select the right screen size for score screen • Lookup theories surounding score screen design. • Test score screen function for problems . • Write score functions in pygame | • Screen must not interfere with the games display • Collected data can be applied to game • tests should be succesfull and function need to work • Test canvas is a succes • Code doesnt cause problems with other game functions
3 | As a developer i want a prototype of the game pause menu so i can halt the game if needed. | H | 3 hours | • Select the right screen size for pause screen • Lookup theories surounding pause screen design. • Test pause screen function for problems . • Write pause functions in pygame | • Screen must interfere with the games display • Collected data can be applied to game • tests should be succesfull and function need to work • Pause has to stop the game temporarily but not score • Code doesnt cause problems with other game functions such as progression
4 | As a Developer i want a prototype of the game obstacles so i can challenge the players progress | H | 10 hours | • search for theories surrounding game obstacles • studie obstacle behaviour with sprites • studie how obstacles effect the other code functions • Concept code for obstacles • make a base system file with obstacles • test obstacles • Rewrite code to support | •theories can be applied to my game • studies support my sprites and basic function for obstacle works • Rewritten code supports obstacles • import file function works for obstacle file • Basic Character movements work

## Sprint 3
Sprint backlog 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a user, I want a menu screen , so i have an option to exit the game. | H | 3 hours | • Select the right screen size for menu • Lookup theories surounding screen design. • Test menu function for problems . • Write menu size in pygame | • Screen must not interfere with the games display • Collected data can be applied to game • tests should be succesfull and function need to work • Test canvas is a succes • Code doesnt cause problems with other game functions
2 | As a user, i want visually stunning background graphics so i can enjoy the artstyle of the games. | H | 5 hours | • search for backgrounds that fit the theme of the game • studie obstacle behaviour with sprites • studie how obstacles effect the other code functions • Concept code for obstacles • Add background image to the sprites file | • background must not interfere with the games display • Collected data can be applied to game • tests should be succesfull and function of background need to work • Test game with new background should be flawless • Code of background doesnt cause problems with other game functions
3 | As a developer i want a pause menu so i can halt the game if needed. | H | 3 hours | • Select the right screen size for pause screen • Lookup theories surounding pause screen design. • Test pause screen function for problems . • Write pause functions in pygame | • Screen must interfere with the games display • Collected data can be applied to game • tests should be succesfull and function need to work • Pause has to stop the game temporarily but not score • Code doesnt cause problems with other game functions such as progression
4 | As a player i want i visually stunning character so i can be represented as a gamecharacter. | H | 10 hours | • search for sprite based images for character • studie obstacle behaviour with sprites • resize character to fit the game • make a map and add character image in it • test character • Rewrite code to support character | •character is the right size and fits inside the screen • character matches the theme of the game • import image file works properly • Basic Character looks visually stunning
5 | As a developer i want bugs fixed so the player can enjoy the game. | H | 40 hours | • search for bugs in the code and look what causes them • studie obstacle behaviour with sprites • studie how obstacles effect the other code functions and fix errors • test new code • Rewrite code to support the extra lines of code | • bugs surrounding code are fixed • test code is successfull • studie how obstacles effect the other code functions • test of new code is successfull and works properly
6 | As a player i want one game menu ,so i can access all the minigames from one place. | H | 20 hours | • search for bugs in the code and look what causes all games to not load • studie videos surrounding adding mutiple types of code to one file • studie how obstacles effect the other code functions and fix errors • Rewrite code to support all games at the same time | • search for bugs in the code and look what causes all games to not load can be applied to our game menue • Rewritten code to support all games at the same time works
7 | As a player i want ambient noise , i can enjoy the game sounds while playing the game in peace. | H | 2 hours | • Search for music that fits the team of the game • Add sound fuction to the game settings file | • Ambient noice volume is mild and not distracting to the player • Add sound fuction plays music when game starts