## SprintInfo
Start Date | 2018-03-06 | Enter the start date for the sprint
End Date | 2018-03-20 | Enter the ending date for the sprint
Elapsed Days | 11
Holidays | 0 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 11
Number of Devs | 6
Utilization | 30% | Enter a value for the utilization of the team
Available Dev Hours | 158.4
Daily Dev Hours | 14.4

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status
1 | 1 | 8 | Menu Implementeren | Sina+Koen | 0 | Completed
1 | 5 | 8 | Basis app opzetten | Sina+Koen | 0 | Completed
1 | 1 | 3 | Help scherm implementeren | Sina+Koen | 0 | Completed
1 | 4 | 2 | ERD voor de database maken | Malaz+Mitchel | 0 | Completed
1 | 5 | 2 | Quieres schrijven om data vanaf Excel naar de database te verwerken | Malaz+Mitchel | 0 | Completed
1 | 3 | 8 | Quieres schrijven om tabellen te genereren | Malaz+Mitchel | 0 | Completed
1 | 1 | 6 | Tabellen maken in Excel | iedereen | 0 | Completed
1 | 3 | 5 | Verschillende diagrammen opzoeken | Chofni+Joseph | 0 | Completed
1 | 3 | 5 | Brainstormen naar geschikte diagrammen voor filters | Chofni+Joseph | 0 | Completed
1 | 5 | 3 | Mockup diagrammen als voorbeeld | Chofni+Joseph | 3 | Completed
| 2 | 8 | manier om grafieken te implementeren opzoeken | Malaz+Mitchel | 0 | Completed
| 3 |  |  |  | 0
| 4 |  |  |  | 0
Total |  | 58 |  |  | 3

## BurnDownTable
Work Day | Target Burn Down | Forecast Burn Down | Actual Burn Down
0 | 58 | 58 | 56
1 | 52.7273 | 53 | 48
2 | 47.4545 | 47 | 45
3 | 42.1818 | 42 | 38
4 | 36.9091 | 37 | 35
5 | 31.6364 | 32 | 28
6 | 26.3636 | 26 | 22
7 | 21.0909 | 21 | 20
8 | 15.8182 | 16 | 13
9 | 10.5455 | 11 | 10
10 | 5.2727 | 5 | 3
Note on A2: PowerUps for Excel: Create one row per day in the sprint.